## Sprint 1
Sprint Name: | Sprint 1
Goal: | Create a working command-line application (CLI) that supports basic user management for the BookstoreCLI application using Core Java.
Tasks:
Task 1 | Describe the Project Architecture with UML Structural and Behavioral Diagrams
Status: | TODO
SubTask 1 | Create the Use Case Diagram for BookstoreCLI
Description: Diagram showing how users (Admin and Normal) interact with the system.
SubTask 2 | Create Activity Diagrams for:
Create User Module
Description: This activity diagram will capture the process of creating users at the beginning of the application.
Diagram Steps:
Start
Initialize User Array
Add Admin User to the User Array
Add Normal User to the User Array
End
Login User Module
Description: This activity diagram will show the user authentication process once the application is running.
Diagram Steps:
Start
Display Login Prompt
User Enters Credentials
Check Credentials
If Credentials Valid:
Display User Options (Admin or Normal User based on role)
Else:
Display Error Message
End
SubTask 3 | Create BookstoreCLI Class Diagram:
Classes to Include:
User
Description: Abstract class for common user attributes and methods.
AdminUser
Description: Inherits from User, represents an admin user.
NormalUser
Description: Inherits from User, represents a normal user.
UserInterface
Description: Interface for user-related methods.
UserRole
Description: Enum for user roles (ADMIN, NORMAL_USER).
UserController
Description: Handles user-related actions and interactions.
UserDAO
Description: Data Access Object for managing user data persistence.
UserService
Description: Provides business logic and interactions with UserDAO.
Relationships to Show:
Inheritance: AdminUser and NormalUser inherit from User.
Implementation: AdminUser and NormalUser implement UserInterface.
Associations: UserController interacts with UserService and UserDAO.
Dependency: UserService depends on UserDAO for data access.
Dependency: UserDAO depends on User for the model object.
SubTask 4 | Create Sequence Diagrams for:
Create User Module
Description: This sequence diagram will detail the interactions involved in creating user instances at the application start-up.
Diagram Steps:
Main initializes
Main calls addUser method for AdminUser
AdminUser instance created and added to User Array
Main calls addUser method for NormalUser
NormalUser instance created and added to User Array
Login User Module
Description: This sequence diagram will show the steps involved in user login authentication.
Diagram Steps:
User selects "Login"
Main displays login prompt
User enters username and password
Main calls authenticate method
authenticate searches User Array
If User found:
displayOptions method called based on user role
Else:
Main displays error message
SubTask 5 | Create Package Diagram
Description: This diagram will represent the organization of different packages within the BookstoreCLI application, showing their relationships and dependencies.
SubTask 6 | Create Entity-Relationship (ER) Diagram
Description: This subtask involves creating an ER diagram based on the provided database schema to visualize the relationships between the entities in the BookstoreCLI application.
Entities: Users, Books, Orders, and Order Items with their respective attributes.
Relationships:
A User can place zero or many Orders.
An Order can contain zero or many Order Items.
Each Order Item includes one Book.
Done: | UML model project uploaded to Bitbucket repo in PDF format.
Task 2 | Create a Maven Project in IntelliJ
Status: | TODO
SubTask 1 | Write dependencies in the pom.xml for a Java application.
SubTask 2 | Add the necessary plugins for building and packaging the project.
Done: | Scaffold project in IntelliJ workspace.
Task 3 | Implement the Java Application
Status: | TODO
SubTask 1 | Create Java classes and interface according to the UML model with methods for basic operations.
Done: | Passing basic CLI functionality.
Task 4 | Check Project artifacts and code into BitBucket
Status: | TODO
SubTask 1 | Push the code base and project artifacts to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.

## Sprint 2
Sprint Name: | Sprint 2
Goal: | Enhance the CLI application with user friendly error messages. Introduce JUnit 5 tests with Mockito.
Tasks:
Task 1 | Describe the Project Architecture with UML Structural and Behavioral Diagrams
Status: | TODO
SubTask 1 | Create the Use Case Diagram for BookstoreCLI
Description: Diagram showing how users (Admin and Normal) interact with the system, including new features introduced in Sprint 2.
SubTask 2 | Create Activity Diagrams for:
Create User Module
Description: This activity diagram will capture the process of creating users at the beginning of the application, now including interactions with UserService, UserDAO, and BookstoreHelper.
Diagram Steps:
Start
Initialize User Array
Add Admin User to the User Array using UserService and UserDAO
Add Normal User to the User Array using UserService and UserDAO
End
Login User Module
Description: This activity diagram will show the user authentication process once the application is running, incorporating UserService and UserDAO.
Diagram Steps:
Start
Display Login Prompt
User Enters Credentials
Check Credentials using UserService and UserDAO
If Credentials Valid:
Display User Options (Admin or Normal User based on role)
Else:
Display Error Message
End
SubTask 3 | Update BookstoreCLI Class Diagram:
Classes to Include:
User
Description: Abstract class for common user attributes and methods.
AdminUser
Description: Inherits from User, represents an admin user.
NormalUser
Description: Inherits from User, represents a normal user.
UserInterface
Description: Interface for user-related methods.
UserRole
Description: Enum for user roles (ADMIN, NORMAL_USER).
UserController
Description: Handles user-related actions and interactions.
UserDAO
Description: Data Access Object for managing user data persistence.
UserService
Description: Provides business logic and interactions with UserDAO.
Book
Description: Represents a book entity in the system.
BookController
Description: Handles book-related actions and interactions.
BookDAO
Description: Data Access Object for managing book data persistence.
BookstoreHelper
Description: Utility class for handling various bookstore-related operations.
BookstoreService
Description: Provides business logic and interactions with BookDAO.
Relationships to Show:
Inheritance: AdminUser and NormalUser inherit from User.
Implementation: AdminUser and NormalUser implement UserInterface.
Associations: UserController interacts with UserService and UserDAO.
Dependency: UserService depends on UserDAO for data access.
Associations: BookController interacts with BookstoreService and BookDAO.
Dependency: BookstoreService depends on BookDAO for data access.
Utility: BookstoreHelper interacts with BookController and BookstoreService.
SubTask 4 | Create Sequence Diagrams for:
Create User Module
Description: This sequence diagram will detail the interactions involved in creating user instances at the application start-up, incorporating UserService and UserDAO.
Diagram Steps:
Main initializes
Main calls addUser method for AdminUser using UserService using UserService
AdminUser instance created and added to User Array
Main calls addUser method for NormalUser
UserService calls UserDAO to persist NormalUser
NormalUser instance created and added to User Array
Login User Module
Description: This sequence diagram will show the steps involved in user login authentication, incorporating UserService and UserDAO.
Diagram Steps:
User selects "Login"
Main displays login prompt
User enters username and password
Main calls authenticate method using UserService
UserService calls UserDAO to authenticate user
If User found:
displayOptions method called based on user role
Else:
Main displays error message
SubTask 5 | Create Package Diagram
Description: This diagram will represent the organization of different packages within the BookstoreCLI application, showing their relationships and dependencies.
Done: | UML model project uploaded to Bitbucket repo in PDF format.
Task 2 | Upgrade the Maven project to factor in error handling, DAO classes and unit tests.
Status: | TODO
SubTask 1 | Follow the TDD approach to refactor the application to include the Javava classes and interface according to the UML model with methods for basic operations.
SubTask 2 | Code the unit tests using Junit 5 and Mockito.
Done: | Passing upraded CLI functionality.
Code coverage close to 90%.
Task 3 | Check Project artifacts and code into BitBucket
Status: | TODO
SubTask 1 | Push the code base and project artifacts to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.

## Sprint 3
Sprint Name: | Sprint 3
Goal: | Refactor and enhance the "BookstoreCLI" application with a focus on security, new features, and advanced development practices.
Tasks:
Task 1 | Describe the Project Architecture with UML Structural and Behavioral Diagrams
Status: | TODO
SubTask 1 | Create the Use Case Diagram for BookstoreCLI
Description: Diagram showing how users (Admin and Normal) interact with the system, including new features introduced in Sprint 3.
SubTask 2 | Create the Use Case Diagram for the Book Order Feature
Description: Diagram showing how Normal Users interact with the system to cancel their book orders, including new classes/interfaces introduced in Sprint 3.
SubTask 3 | Create Activity Diagrams for:
Secure Data Storage Module
Description: This activity diagram will capture the process of securely storing Personally Identifiable Information (PII) in the PostgreSQL database in encrypted format.
Diagram Steps:
Start
Retrieve PII
Encrypt PII using UserDAO
Store encrypted PII in PostgreSQL database
End
Role-Based Security Module
Description: This activity diagram will show the process of implementing role-based authentication and authorization.
Diagram Steps:
Start
User Logs In
Retrieve User Role using UserService
Check Permissions based on Role using UserService
Grant or Deny Access
End
Book Order Module
Description: This activity diagram will capture the process of placing an order, removing a book from an order, completing an order, and viewing all orders by Normal Users.
Diagram Steps:
Start
User Logs In
Retrieve User Role using UserService
Check Permissions based on Role using UserService
Grant or Deny Access
End
Browse Books
=>User selects books to add to the order
=>Add selected books to the order
View Order
User views current order details
Option to remove a book from the order
=>If removing a book:
=>Select book to remove
=>Remove book from the order
Complete Order
=>Proceed to Checkout
=>Confirm Order Details
=>Save Order to Database
View Order History
=>Retrieve all past orders from the database
End
Admin Data Loading Module
Description: This activity diagram will show how admin users can load data into the PostgreSQL database from a CSV file.
Diagram Steps:
Start
Admin Logs In
Upload CSV File
Parse CSV Data
Insert Data into PostgreSQL
End
SubTask 4 | Update BookstoreCLI Class Diagram:
Classes to Include:
UserDAO
Description: Handles encryption and decryption of PII, manages user data persistence.
UserService
Description: Handles user authentication and session management, validates user credentials, and checks permissions based on roles.
OrderService
Description: Manages the creation, retrieval, and updating of book orders, interacts with the database to store and retrieve order information.
OrderController
Description: Handles user requests related to book orders, interacts with the OrderService, ensures correct data is passed between the user interface and service layer.
CSVUtil
Description: Utilizes Java NIO's FileChannel, Buffer, and Path classes to read from and write to CSV files, facilitates loading data into the PostgreSQL database from CSV files, handles file operations efficiently.
Relationships to Show:
Inheritance: AdminUser and NormalUser inherit from User.
Implementation: AdminUser and NormalUser implement UserInterface.
Associations: UserController interacts with UserService and UserDAO.
Dependency: UserService depends on UserDAO for data access.
Associations: BookController interacts with BookstoreService and BookDAO.
Dependency: BookstoreService depends on BookDAO for data access.
Utility: BookstoreHelper interacts with BookController and BookstoreService.
Associations: OrderController interacts with OrderService and OrderDAO.
Utility: CSVUtil interacts with BookController and BookDAO.
Dependency: UserDAO handles encryption and decryption of PII.
SubTask 5 | Create Sequence Diagrams for:
Secure Data Storage Module
Description: This sequence diagram will detail the interactions involved in securely storing PII, incorporating UserDAO.
Diagram Steps:
UserController calls UserDAO to encrypt PII
UserDAO encrypts PII and returns encrypted data
UserController calls UserDAO to store encrypted PII in the database
Role-Based Security Module
Description: This sequence diagram will show the steps involved in role-based authentication and authorization, incorporating UserService.
Diagram Steps:
User logs in with credentials
UserService calls UserDAO to validate credentials
UserDAO returns user details and role
UserService assigns user session and role
UserService checks user permissions based on role
UserService grants or denies access
Admin Data Loading Module
Description: This sequence diagram will detail the interactions involved in loading data from a CSV file into the PostgreSQL database, incorporating CSVUtil.
Diagram Steps:
Admin uploads CSV file
CSVUtil reads and parses CSV data
CSVUtil calls BookDAO to insert data into the PostgreSQL database
Book Order Module
Description: This sequence diagram will detail the interactions involved in placing a book order, removing a book from an order, completing an order, and viewing all orders by Normal Users, incorporating OrderService and OrderDAO.
Diagram Steps:
NormalUser browses books
NormalUser adds books to cart
NormalUser views current order details
NormalUser proceeds to checkout
NormalUser confirms order
OrderController calls OrderService to save the order
OrderService calls OrderDAO to store order information in the database
NormalUser views order history
NormalUser selects an order to cancel
NormalUser confirms cancellation
OrderController calls OrderService to update the order status
OrderService calls OrderDAO to update order information in the database
SubTask 6 | Create Collaboration Diagram for:
Role-Based Security Module
Description: This collaboration diagram will illustrate the interactions between system components during role-based authentication and authorization, showcasing how objects communicate to achieve this functionality.
Diagram Steps:
User initiates the process by sending a login request to Main.
Main forwards the authentication request (with username and password) to UserService.
UserService sends a request to UserDAO to validate the credentials by fetching user details based on the username.
UserDAO returns the user details and associated role to UserService.
UserService verifies the user's role and assigns the appropriate session.
UserService checks user permissions according to the assigned role.
UserService informs Main whether the access is granted or denied.
Main communicates the result to User, displaying options or denying access based on the user's role.
Objective: To clearly outline the sequence of interactions and the messages exchanged between User, Main, UserService, and UserDAO in the role-based authentication and authorization process.
Expected Output: A collaboration diagram showing:-
The sequence of calls and message exchanges among the components.
The structure of the interactions, emphasizing the flow of control and data.
SubTask 7 | Create Package Diagram
Description: This diagram will represent the organization of different packages within the BookstoreCLI application, showing their relationships and dependencies.
Done: | UML model project uploaded to Bitbucket repo in PDF format.
Task 2 | Upgrade the Maven project to incorporate new security features and admin functionalities.
Status: | TODO
SubTask 1 | Follow the TDD approach to refactor the application to include the Java classes and interfaces according to the UML model with methods for enhanced operations.
Description:
Apply Test-Driven Development (TDD) to enhance the application, ensuring each new feature has corresponding tests before implementation.
Incorporate classes and interfaces to manage new functionalities like secure data storage, role-based security, and admin data loading.
SubTask 2 | Code the unit tests using Junit 5 and Mockito.
Description:
Develop unit tests for all major components using JUnit 5.
Use Mockito to create mock objects for testing database operations and user interactions.
Done: | Passing upraded CLI functionality.
Code coverage close to 90%.
Task 3 | Implement Behavior-Driven Development (BDD) tests using Cucumber for Java.
Status: | TODO
SubTask 1 | Write Gherkin syntax scenarios to define the behavior of the application.
Description:
Develop detailed scenarios in Gherkin syntax to define the expected behavior of the application, covering new features and enhancements introduced in Sprint 3.
SubTask 2 | Create step definitions to map Gherkin steps to Java methods.
Description:
Develop step definitions to map Gherkin steps to Java methods, allowing automated execution of BDD tests.
SubTask 3 | Integrate Cucumber tests with JUnit 5 to run BDD tests as part of the test suite.
Description:
Ensure Cucumber tests are integrated with JUnit 5 to run BDD tests as part of the test suite, capturing detailed reports of test results.
SubTask 4 | Generate Cucumber BDD reports with Serenity.
Description:
Integrate Serenity with Cucumber to generate comprehensive reports for BDD tests.
Configure Serenity to capture detailed information about test execution and results.
Done: | All BDD scenarios and acceptance criteria met, and test results captured in detailed reports generated by Serenity.
Task 4 | Check Project artifacts and code into BitBucket
Status: | TODO
SubTask 1 | Push the code base and project artifacts to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.

## Sprint 4
Sprint Name: | Sprint 4
Goal: | Reengineer the 'BookstoreApp' project utilizing Spring Boot and Spring REST to incorporate advanced features, enhance security, and ensure robust functionality
Tasks:
Task 1: | Describe the Project Architecture with UML Structural and Behavioral Diagrams
Status: | TODO
SubTask 1 | Create the Use Case Diagram for BookstoreApp
Description: Diagram showing how users (Admin and Normal) interact with the system.
SubTask 2 | Create the Use Case Diagram for the User Authentication Feature
Description: Diagram showing how users interact with the system to log in and manage their sessions.
SubTask 3 | Create Activity Diagrams for:
Secure Data Storage Module
Description: This activity diagram will capture the process of securely storing Personally Identifiable Information (PII) in the PostgreSQL database in encrypted format.
Diagram Steps:
Start
Retrieve PII
Encrypt PII using UserDAO
Store encrypted PII in PostgreSQL database
End
Role-Based Security Module
Description: This activity diagram will show the process of implementing role-based authentication and authorization.
Diagram Steps:
Start
User Logs In
Retrieve User Role using UserService
Check Permissions based on Role using UserService
Grant or Deny Access
End
Order Management Module
Description: This activity diagram will capture the process of placing an order, removing a book from an order, completing an order, and viewing all orders by Normal Users.
Diagram Steps:
Start
User Logs In
Browse Books
=>User selects books to add to the order
=>Add selected books to the order
View Order
User views current order details
Option to remove a book from the order
=>If removing a book:
=>Select book to remove
=>Remove book from the order
Complete Order
=>Proceed to Checkout
=>Confirm Order Details
=>Save Order to Database
View Order History
=>Retrieve all past orders from the database
End
Admin Data Loading Module
Description: This activity diagram will show how admin users can load data into the PostgreSQL database from a CSV file.
Diagram Steps:
Start
Admin Logs In
Upload CSV File
Parse CSV Data
Insert Data into PostgreSQL
End
SubTask 4 | Create BookstoreApp Class Diagram
Classes to Include:
UserDAO
Description: Handles encryption and decryption of PII, manages user data persistence.
UserService
Description: Handles user authentication and session management, validates user credentials, and checks permissions based on roles.
OrderService
Description: Manages the creation, retrieval, and updating of book orders, interacts with the database to store and retrieve order information.
OrderController
Description: Handles user requests related to book orders, interacts with the OrderService, ensures correct data is passed between the user interface and service layer.
CSVUtil
Description: Utilizes Java NIO's FileChannel, Buffer, and Path classes to read from and write to CSV files, facilitates loading data into the PostgreSQL database from CSV files, handles file operations efficiently.
Relationships to Show:
Inheritance: AdminUser and NormalUser inherit from User.
Implementation: AdminUser and NormalUser implement UserInterface.
Associations:
UserController interacts with UserService and UserDAO.
BookController interacts with BookstoreService and BookDAO.
OrderController interacts with OrderService and OrderDAO.
Dependency:
UserService depends on UserDAO for data access.
BookstoreService depends on BookDAO for data access.
CSVUtil interacts with BookController and BookDAO.
SubTask 5 | Create Sequence Diagrams for:
Secure Data Storage Module
Description: This sequence diagram will detail the interactions involved in securely storing PII, incorporating UserDAO.
Diagram Steps:
UserController calls UserDAO to encrypt PII
UserDAO encrypts PII and returns encrypted data
UserController calls UserDAO to store encrypted PII in the database
Role-Based Security Module
Description: This sequence diagram will show the steps involved in role-based authentication and authorization, incorporating UserService.
Diagram Steps:
User logs in with credentials
UserService calls UserDAO to validate credentials
UserDAO returns user details and role
UserService assigns user session and role
UserService checks user permissions based on role
UserService grants or denies access
Admin Data Loading Module
Description: This sequence diagram will detail the interactions involved in loading data from a CSV file into the PostgreSQL database, incorporating CSVUtil.
Diagram Steps:
Admin uploads CSV file
CSVUtil reads and parses CSV data
CSVUtil calls BookDAO to insert data into the PostgreSQL database
Order Management Module
Description: This sequence diagram will detail the interactions involved in placing a book order, removing a book from an order, completing an order, and viewing all orders by Normal Users, incorporating OrderService and OrderDAO.
Diagram Steps:
NormalUser browses books
NormalUser adds books to cart
NormalUser views current order details
NormalUser proceeds to checkout
NormalUser confirms order
OrderController calls OrderService to save the order
OrderService calls OrderDAO to store order information in the database
NormalUser views order history
NormalUser selects an order to cancel
NormalUser confirms cancellation
OrderController calls OrderService to update the order status
OrderService calls OrderDAO to update order information in the database
SubTask 6 | Create Package Diagram
Description: This diagram will represent the organization of different packages within the BookstoreApp application, showing their relationships and dependencies.
Done: | UML model project uploaded to Bitbucket repo in PDF format.
Task 2 | Update the Maven pom
Status: | TODO
SubTask 1 | Add the dependencies for Spring MVC, Data JPA, Bean Validator Reference Implementation, Security and Database Connector.
SubTask 2 | Add the BCrypt library for password hashing and the libraries for JSON Web Tokens.
SubTask 3 | Add a dependency on Lombok to ease the burden of writing boilerplate code.
Done: | Project configured for Spring REST and Data JPA.
Task 3 | Create the REST Endpoints for the CRUD operations
Status: | TODO
SubTask 1 | Follow the TDD approach to creating the back end tier. You will still be writing the test cases using the framework support in Spring Boot. You need to cover unit tests that can run in isolation as well as integration tests that will bootstrap Spring context before executing tests.
SubTask 2 | The following classes of tests need to be implemented:- a)Smoke and Sanity test:-. Check if the Spring Context is running. b)System test:- It will test the complete application. c)Integration test:- Test the Controller tier together with the Service layer. d)JPA test:- Test the Service tier and the database.
SubTask 3 | Create the Controller, Service and Repository tiers.
SubTask 4 | Create RESTful Web Service endpoints corresponding to each CRUD operation in the Controller tier.
SubTask 5 | Use Status Codes in Error Handling
SubTask 6 | Implement global exception handling with @ControllerAdvice for Controller classes.
SubTask 7 | Use JSR 380 and implement Validation on the model objects.
SubTask 7 | Document the REST API using Swagger 2.0.
Done: | Successfully test the REST API endpoints in Postman.
Task 3 | Create a Performance Test Plan in JMeter
Status: | TODO
SubTask 1 | Do a performance analysis of the application for 100 users. Check that the system satisfies the NFRs and SLAs in the Contextual Problem Statement.
Done: | JMeter shows the test result in Graph format.
Task 4 | Create a Pipeline project in Jenkins to automate the workflow
Status: | TODO
SubTask 1 | Create a Jenkins Pipeline project
SubTask 2 | Checkout/clone the code base from BitBucket repo
SubTask 3 | Compile and package the application
SubTask 4 | Run the JUnit tests and publish the results
SubTask 5 | Add a stage to the pipeline to do a Performance Test with JMeter and publish the results.
SubTask 6 | Add a stage to the pipeline to run the Cucumber BDD tests and publish the results
SubTask 7 | Add a stage to the pipeline to integrate SonarQube with Jenkins.
SubTask 8 | Create a Dockerfile to containerize your Spring Boot application
SubTask 9 | Add a stage to the pipeline to push the image to Docker Hub.
SubTask 10 | Add a stage to the pipeline to pull the image and deploy it to a Tomcat server.
Done: | Build executed successfully in Jenkins with passing test cases
Image created and pushed to Docker Hub.
Unit, Performance and BDD test reports available in Jenkins. Code quality checks available in SonarQube.
Application deployed successfully to Tomcat server.
System satisfies the NFRs and SLAs in the Contextual Problem Statement as well as the Testing requirements.
Task 5 | Check Project artifacts and code into BitBucket
Status: | TODO
SubTask 1 | Push the code base and project artifacts to the appropriate Bitbucket repository. Make sure to include the Swagger API documentation.
Done: | Project artifacts and code available and upto date in the repository.

## Sprint 5
Sprint Name: | Sprint 5
Goal: | Reengineer the "BookstoreCLI" project into a modern web application using React.js, TypeScript, and Next.js, with a focus on integration with REST APIs, implementing ESLint for code quality, and ensuring robust CI/CD and comprehensive testing.
Tasks:
Task 1: | Describe the Project Architecture with a combination of UML diagrams and other types of diagrams that are more specific to front-end architecture and user interactions.
Status: | TODO
SubTask 1 | Create the Use Case Diagram for BookstoreUI
Description: Diagram showing how users (Admin and Normal) interact with the system
SubTask 2 | Create the Component Diagram for BookstoreUI
Purpose: Illustrate the structure and interaction between key components of the Online Bookstore application.
Components to Focus On:
Login Process Component
Component: Login
Purpose: Handles user authentication and role determination (Admin or User).
Interaction: Routes the user to the Admin Dashboard or User Dashboard based on the assigned role.
Admin Dashboard Component
Components:
Add Book
Update Book
Remove Book
Add User
Update User
View All Users
Insert Books from CSV
Purpose: Provides functionalities for managing books and users.
User Dashboard Component
Components:
Browse Books
Search Books
Place Order
View Orders
Add Book to Order
Cancel Order
Complete Order
Purpose: Offers end-user features for browsing, ordering, and managing purchases.
Admin API Service Component
Methods:
addBook
getAllBooks
searchBooks
placeOrder
getOrderById
completeOrder
** Other methods
Purpose: Acts as a central backend service for CRUD operations and data retrieval for Admin features.
** You may also have a LoginAPIService and UserAPI Service components to handle authentication and authorization and CRUD operations for Users. Add them in as appropriate to your design.
SubTask 3 | Extend Component Diagram for Backend Integration
Purpose: Illustrate the connection between the API Service, Spring Boot REST API, and the PostgreSQL database.
Components to Focus On:
Spring Boot REST API Component
Processes incoming requests from the API Service, applies business logic, and coordinates with the database.
Exposes endpoints for CRUD operations on books, users, and orders.
PostgreSQL Database:
Stores and retrieves persistent data for all backend operations.
Handles CRUD operations for entities like books, users, and orders.
Processes to Focus On:
API Service to Spring Boot REST API: Represented as a required interface. This connection enables the consumption of RESTful web services for all application-level interactions.
Spring Boot REST API to PostgreSQL Database: The Spring Boot application connects to the PostgreSQL database to perform all necessary CRUD operations.
Additional Notes:
The API Service acts as a client consuming REST endpoints exposed by the Spring Boot application.
The Spring Boot Application serves as a backend service that processes requests, applies business logic, and interacts with the PostgreSQL database for data persistence.
Diagram Changes:
1. API Service: Add a required interface on the API Service to indicate its dependency on the Spring Boot REST API.
2. Spring Boot Application: Include the Spring Boot Application as a new component connected to both the API Service and PostgreSQL database.
3. Database Integration: Represent the connection between the Spring Boot Application and PostgreSQL database using a direct link, annotated to show CRUD operations.
This task ensures a comprehensive visualization of the system, capturing all interactions from the frontend to the database layer.
SubTask 4 | Create the State Diagrams
Description: Diagram showing how users interact with the system to log in and manage their sessions.
Purpose: Illustrate the states of key components and how they change in response to events.
Components to Focus On:
Cart (e.g., empty, items added, checkout initiated)
Login (e.g., idle, submitting, authenticated, error)
SubTask 5 | Create the Sequence Diagrams
Purpose: Describe the flow of interactions between components for specific features
Processes to Focus On:
User login process (Login -> AuthContext -> API)
Adding a book to the cart (BookList -> Cart -> OrderDetail)
Placing an order (Cart -> PlaceOrder -> API)
SubTask 6 | Create the Activity Diagrams
Purpose: Represent the workflow of particular user interactions or processes.
Activities to Focus On:
Secure data storage (e.g., saving user data with encryption)
Order management (e.g., placing an order, viewing order history)
SubTask 7 | Create Package Diagram
Description: is diagram will illustrate the structure and organization of different modules within the React frontend of the BookstoreUI application, highlighting their relationships and dependencies.
SubTask 8 | Create the User Flow Diagram
Purpose: Visualize the user's journey through the application.
Scenarios to Focus On:
Typical user flow from browsing books to completing an order
Admin user flow for managing books and users
Example User Flow Diagram for a Bookstore Application
Title: User Flow for Placing an Order
1. Start
Entry Point: Homepage
2. Navigation Options
Option 1: Browse Books
Outcome 1: View Book List
Outcome 2: View Book Details
Option 2: Go to Login Page
Outcome 1: Enter Credentials
Outcome 2: Failed Login Attempt
3. Key Actions
Action 1: Add Book to Cart
Sub-action: Choose Quantity
Action 2: View Cart
Sub-action: Edit Cart Items
Action 3: Proceed to Checkout
Sub-action: Enter Payment Details
4. Decision Points
Decision 1: Confirm Order
Outcome 1: Order Placed Successfully
Outcome 2: Order Cancelled
Decision 2: Login Required
Outcome 1: Successful Login
Outcome 2: Redirect to Signup
5. End
Exit Point: Order Confirmation Page
SubTask 9 | Create Wireframes or UI Mockups
Purpose: Provide a visual representation of the application's interface.
Components to Include:
Main pages like BookList, BookDetail, Cart, Login, OrderHistory, ManageUsers
SubTask 10 | Create 4+1 View Architecture Document
Purpose: Summarize the system architecture by utilizing the UML diagrams created in Sprints 4 and 5. This document will provide a comprehensive overview of the application's structure and key components using the 4+1 view model.
Components to Include:
Introduction:
Briefly describe the purpose and scope of the architecture document.
4+1 View Model Overview:
Provide an overview of the 4+1 view model and its significance.
Logical View:
Summarize the logical view of the system, utilizing class diagrams, sequence diagrams, and other relevant UML diagrams created in previous sprints.
Process View:
Detail the process view, highlighting key processes and interactions within the system.
Development View:
Provide insights into the development view, outlining the software components and their organization.
Physical View:
Describe the physical view, showcasing how the system will be deployed across various environments.
Scenarios (Use Case View):
Summarize the use case view, focusing on the primary use cases and their interactions.
Conclusion:
Wrap up the document with a summary of the key points and the overall architecture.
Steps:
1. Review UML Diagrams: Go through the UML diagrams created in Sprints 4 and 5.
2. Draft Introduction: Write the introduction and overview of the 4+1 view model.
3. Document Each View:
Logical View: Include class diagrams, sequence diagrams, etc.
Process View: Detail key processes and interactions.
Development View: Outline software components and their organization.
Physical View: Describe deployment across environments.
Scenarios: Highlight primary use cases and their interactions.
4. Compile the Document: Ensure all views are well-documented and explained.
5. Review and Revise: Ensure completeness, accuracy, and readability.
Done: | UML model project and 4 + 1 View Architecture Document uploaded to Bitbucket repo in PDF format.
Task 2 | Create a React Project with Next.js and TypeScript
Status: | TODO
SubTask 1 | The following screens and features need to be developed: a) Login Page Admins and Normal Users b) Admin Dashboard - Displays list of Admin User options. c) User Dashboard - Displays list of Normal User options. d) Search feature for Admins e) Search feature for Normal Users f) Logout functionality ** Selecting an Admin or Normal User menu option should display the corresponding content in the main content area. The design and structure of the React.js front-end is at your discretion. Pls. ensure all requirements are met.
SubTask 2 | Introduce a 3 second delay into the application when the list of records is being retrieved, or when a record is being updated or added.
SubTask 3 | The pages displaying the list of records and save/update of a record should show a Spinner or Progress Bar while the page is being displayed or the records are being retrieved. The Spinner or Progress Bar should disappear when the page is rendered.
SubTask 4 | The page(s) where a record is added or updated should have the Save/Update button disabled while a new record is being saved or updated. The label on the button should change from 'Save' to 'Saving..'.
SubTask 5 | On successful save or update, the user should only then be navigated to the list of records.
SubTask 6 | On unsuccessful save or update, the user should remain on the page. A Toast notification should be displayed with a user friendly error message.
SubTask 7 | On Delete, the user must immediately be navigated to the list of records(Optimistic Deletes) unless the Delete buttons are on the same page; in which case the page simply needs to be reloaded to display the updated list.
SubTask 8 | The notification for an unsuccessful Create,Update or Delete action will not have a display interval. It will need to be manually closed by the end user.
SubTask 9 | Use Toast Notifications or SweetAlert or any library of your choosing to display alerts and messages to a user. It can be a success message, warning message, or custom message. You may set the display interval to 2-3 seconds.
SubTask 10 | Create the Dockerfile for the ReactJS app.
Done: | Full featured working application running locally.
Task 3 | BDD Using Cucumber
Status: | TODO
SubTask 1 | Use behavior-driven development (BDD) to define clear, unambiguous requirements
Description: Gather requirements and translate them into BDD scenarios using Gherkin syntax. These scenarios should clearly define the expected behavior of the application in an understandable manner.
SubTask 2 | Turn these requirements into automated acceptance tests.
Description: Implement the defined BDD scenarios as automated acceptance tests using Cucumber. Ensure these tests are integrated into the CI/CD pipeline for continuous verification.
Done: | Verification of application’s behavior: Ensure that the application's behavior matches the expected outcomes defined in the BDD scenarios.
Documentation of each feature: Generate detailed documentation for each feature, based on the BDD scenarios and test results.
Task 4 | Create a Performance Test Plan in JMeter
Status: | TODO
SubTask 1 | Do a performance analysis of the application for 100 users. Check that the system satisfies the NFRs and SLAs in the Contextual Problem Statement.
Done: | JMeter shows the test result in Graph format.
Task 5 | Create the Jenkins Pipeline for ReactJs app
Status: | TODO
SubTask 1 | Follow the steps outlined in Week 4 - Task 3 to create the Jenkins Pipeline for the React JS app.
Description: This subtask involves setting up the Jenkins Pipeline for the ReactJS app as previously defined. This would include steps such as checking out the code, installing dependencies, building the application, and running tests.
SubTask 2 | Add a stage to the pipeline to serve up the BookstoreUI app on an NGINX server running locally.
Description: This subtask involves configuring a stage in the Jenkins Pipeline that deploys the built ReactJS application to an NGINX server running on your local machine. This will include steps to build the Docker image, push it to Docker Hub, and then pull and run it on the local NGINX server.
Done: | Build executed successfully in Jenkins with passing test cases
Image created and pushed to Docker Hub.
Unit, Performance and BDD test reports available in Jenkins. Code quality checks available in SonarQube.
Application deployed successfully to NGINX server.
System satisfies the NFRs and SLAs in the Contextual Problem Statement as well as the Testing requirements.
Login Page should display when hitting the BookstoreUI app's Base URL.
Task 6 | Check Project artifacts and code into BitBucket
Status: | TODO
SubTask 1 | Push the code base and project artifacts to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.